## WBS with Gantt Chart - BLANK
PROJECT TITLE | Sistem Informasi Cuci Sepatu Sscleaner
PROJECT MANAGER | Naufal Rifqi
COMPANY NAME | Kelompok 1
DATE | 2023-09-26 | [5 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | % of TASK | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[6 empty] | COMPLETE | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Analisa dan Desain Sistem |  | 2023-09-26 | 2023-10-16
1.1 | Menganalisa Sistem Kepegawaian dengan melakukan wawancara kepada pihak yang ditunjuk | Ghaniy Ihdi, Naufal Rifqi | 2023-09-26 | 2023-10-03 | 7 | 100%
1.2 | Project Charter | Alief Syahputra | 2023-10-03 | 2023-10-09 | 6 | 85%
1.3 | Gantt Chart | Alief Syahputra | 2023-10-09 | 2023-10-16 | 7 | 20%
1.4 | Work Breakdown System(WBS) | Alief Syahputra | 2023-10-09 | 2023-10-16 | 7 | 10%
1.5 | Membuat Perth | Ghaniy Ihdi |  |  |  | 0%
1.6 | Membuat Process Spesification | Ghaniy Ihdi |  |  |  | 0%
1.7 | Dokumentasi Analisa & Desain | Ghaniy Ihdi |  |  |  | 0%
2 | Desain Aplikasi
2.1 | Membuat Desain Input | Alessandro |  |  |  | 0%
2.2 | Membuat Desain Report | Alessandro |  |  |  | 0%
2.3 | Dokumentasi Desain Aplikas | Alessandro |  |  |  | 0%
3 | Pembuatan Program
3.1 | Programming (Back End & Front End) | Rifqi Feliantyto |  |  | 40 | 0%
3.2 | Dokumentasi Program (Back End & Front End) | Rifqi Feliantyto |  |  | 5 | 0%
4. | Writer & Tester
4.1 | Melakukan Test Program | Alief Syahputra |  |  |  | 0%
4.2 | Memberikan catatan list perbaikan | Alief Syahputra |  |  |  | 0%
4.3 | Dokumentasi Testing Program | Alief Syahputra |  |  |  | 0%
5 | Instalasi Program
5.1 | Setting Infrastruktur dan Software pendukung | Rifqi Feliantyto |  |  |  | 0%
5.2 | Instalasi Program ke Client | Rifqi Feliantyto |  |  |  | 0%
6 | Training User / SDM | Rifqi Feliantyto |  |  |  | 0%
6.1 | Melakukan Pelatihan | Rifqi Feliantyto |  |  |  | 0%
7 | Dokumetasi
7.1 | Desain Spesifikasi Sistem | Alessandro |  |  |  | 0%
7.2 | Dokumentasi SOP | Alief Syahputra |  |  |  | 0%
7.3 | Dokumentasi Administrasi Proyek | Alief Syahputra |  |  |  | 0%
7.4 | Dokumentasi User & Admin Guide + Dokumen Program | Alief Syahputra |  |  |  | 0%
7.5 | Dokumentasi Manajemen Proyek | Alief Syahputra |  |  |  | 0%
8 | Maintenance
8.1 | Pemeliharaan dan Perbaikan Sistem | Rifqi Feliantyto |  |  |  | 0%
9. | Administrasi
9.1 | Melakukan Administrasi Proyek & Mendokumentasikan | Alief Syahputra |  |  |  | 0%