## WBS with Gantt Chart - BLANK
WORK BREAKDOWN STRUCTURE WITH GANTT CHART TEMPLATE
PROJECT TITLE | Pembuatan Website Di Graha Coffee & Eatery
PROJECT MANAGER | Ridha Akmal
COMPANY NAME | Kelompok 3
DATE | 2023-09-26 | [5 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | % of TASK | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[6 empty] | COMPLETE | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Analisa dan Desain Sistem |  | 26-9-2023 | 2023-10-10
1.1 | Menganalisa Sistem Kepegawaian dengan melakukan wawancara kepada pihak yang ditunjuk | Ridha Akmal | 2023-11-10 | 13-10-2023 | 3 | 100%
1.2 | Project Charter | Fajar Febriansyah | 14-10-2023 | 15-10-2023 | 7 | 85%
1.3 | Gantt Chart | Johanda Lobianto | 16-10-2023 | 17-10-2023 | 7 | 80%
1.4 | Membuat Data Flow Diagram (DFD) Levelled |  | 17-10-2023 | 17-10-2023 | 1 | 0%
1.5 | Membuat Entity Relationship Diagram (ERD) |  | 20-10-2023 | 20-10-2023 | 1 | 0%
1.6 | membuat process spesification |  | 21-10-2023 | 21-10-2023 | 1 | 0%
1.7 | Dokumentasi Analisa & Desain Sistem |  | 22-10-2023 | 23-10-2023 | 2 | 0%
2 | Desain Website |  | 23-10-2023 | 29-10-2023
2.1 | Membuat Desain Input |  | 23-10-2023 | 24-10-2023 | 2 | 0%
2.2 | Membuat Desain Report |  | 25-10-2023 | 26-10-2023 | 2 | 0%
2.3 | Dokumentasi Desain Aplikasi |  | 27-10-2023 | 29-10-2023 | 3 | 0%
3 | Pembuatan Program |  | 30-10-2023 | 23-11-2023
3.1 | Programming (Back end & Front end) |  | 30-10-2023 | 18-11-2023 | 20 | 0%
3.2 | Dokumentasi Program (Back end & Front end) |  | 19-11-2023 | 23-11-2023 | 5 | 0%
4 | Testing Program |  | 24-11-2023 | 28-11-2023
4.1 | melakukan test terhadap program |  | 24-11-2023 | 25-11-2023 | 2 | 0%
4.2 | memberikan list catatan perbaikan |  | 26-11-2023 | 26-11-2023 | 1 | 0%
4.3 | dokumentasi testing program |  | 27-11-2010 | 28-11-2023 | 2 | 0%
5 | instalasi program |  | 2023-01-12 | 2023-02-12
5.1 | setting infrastruktur dan software pendukung |  | 2023-01-12 | 2023-01-12 | 1 | 0%
5.2 | instalasi program ke client |  | 2023-02-12 | 2023-02-12 | 1 | 0%
6 | training user / SDM |  | 2023-05-12 | 2023-05-12
6.1 | melakukan pelatihan |  | 2023-05-12 | 2023-05-12 | 2 | 0%
7 |  |  | 30-09-2023 | 30-12-2023
7.1 | desain dan spesifikasi sistem |  | 30-09-2023 | 19-10-2023 | 15
7.2 | dokumentasi Home |  | 20-10-2023 | 2023-02-11 | 10
7.3 | dokumentasi daftar menu |  | 2023-03-11 | 14-11-2023 | 10
7.4 | dokumentasi membership |  | 15-11-2023 | 19-11-2023 | 5
7.5 | dokumentasi tentang kami & kontak |  | 20-11-2023 | 30-11-2023 | 10
8 | Maintenance |  | 2024-05-01 | 25-01-2024
8.1 | pemeliharaan dan perbaikan sistem |  | 2024-05-01 | 25-01-2024 | 20
9 | Administrasi |  | 2024-05-01 | 30-01-2024
9.1 | Melakukan Administrasi Proyek & Mendokumentasikannya |  | 2024-05-01 | 30-01-2024 | 31