## WBS with Gantt Chart - BLANK
WORK BREAKDOWN STRUCTURE WITH GANTT CHART TEMPLATE
PROJECT TITLE | Pembuatan Website Di Graha Coffee & Eatery
PROJECT MANAGER | Ridha Akmal
COMPANY NAME | Kelompok 3
DATE | 2023-09-26 | [5 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | % of TASK | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[6 empty] | COMPLETE | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Analisa dan Desain Sistem |  | 2023-09-26 | 2023-10-10
1.1 | Menganalisa Sistem Kepegawaian dengan melakukan wawancara kepada pihak yang ditunjuk | Ridha Akmal | 2023-09-26 | 2023-10-03 | 3 | 100%
1.2 | Project Charter | Fajar Febriansyah | 2023-10-03 | 2023-10-09 | 7 | 85%
1.3 | Gantt Chart | Johanda Lobianto | 2023-10-09 | 2023-10-16 | 7 | 20%
1.4 | Membuat Data Flow Diagram (DFD) Levelled |  | 2023-10-16 | 2023-10-16 | 1 | 0%
1.5 | Membuat Entity Relationship Diagram (ERD) |  | 2023-10-17 | 2023-10-17 | 1 | 0%
1.6 | membuat process spesification |  | 2023-10-21 | 2023-10-21 | 1 | 0%
1.7 | Dokumentasi Analisa & Desain Sistem |  | 2023-10-22 | 2023-10-23 | 2 | 0%
2 | Desain Website |  | 2023-10-23 | 2023-10-29
2.1 | Membuat Desain Input |  | 2023-10-23 | 2023-10-24 | 2 | 0%
2.2 | Membuat Desain Report |  | 2023-10-25 | 2023-10-26 | 2 | 0%
2.3 | Dokumentasi Desain Aplikasi |  | 2023-10-27 | 2023-10-29 | 3 | 0%
3 | Pembuatan Program |  | 2023-10-30 | 2023-11-23
3.1 | Programming (Back end & Front end) |  | 2023-10-30 | 2023-11-18 | 20 | 0%
3.2 | Dokumentasi Program (Back end & Front end) |  | 2023-11-19 | 2023-11-23 | 5 | 0%
4 | Testing Program |  | 2023-11-24 | 2023-11-28
4.1 | melakukan test terhadap program |  | 2023-11-24 | 2023-11-25 | 2 | 0%
4.2 | memberikan list catatan perbaikan |  | 2023-11-26 | 2023-11-26 | 1 | 0%
4.3 | dokumentasi testing program |  | 2010-11-27 | 2023-11-28 | 2 | 0%
5 | instalasi program |  | 2023-12-01 | 2023-12-02
5.1 | setting infrastruktur dan software pendukung |  | 2023-12-01 | 2023-12-01 | 1 | 0%
5.2 | instalasi program ke client |  | 2023-12-02 | 2023-12-02 | 1 | 0%
6 | training user / SDM |  | 2023-12-05 | 2023-12-05
6.1 | melakukan pelatihan |  | 2023-12-05 | 2023-12-05 | 2 | 0%
7 |  |  | 2023-09-30 | 2023-12-30
7.1 | desain dan spesifikasi sistem |  | 2023-09-30 | 2023-10-19 | 15
7.2 | dokumentasi Home |  | 2023-10-20 | 2023-11-02 | 10
7.3 | dokumentasi daftar menu |  | 2023-11-03 | 2023-11-14 | 10
7.4 | dokumentasi membership |  | 2023-11-15 | 2023-11-19 | 5
7.5 | dokumentasi tentang kami & kontak |  | 2023-11-20 | 2023-11-30 | 10
8 | Maintenance |  | 2024-01-05 | 2024-01-25
8.1 | pemeliharaan dan perbaikan sistem |  | 2024-01-05 | 2024-01-25 | 20
9 | Administrasi |  | 2024-01-05 | 2024-01-30
9.1 | Melakukan Administrasi Proyek & Mendokumentasikannya |  | 2024-01-05 | 2024-01-30 | 31