## WBS with Gantt Chart - BLANK
WORK BREAKDOWN STRUCTURE WITH GANTT CHART TEMPLATE
PROJECT TITLE | Pembuatan Website Di Graha Coffee & Eatery
PROJECT MANAGER | Ridha Akmal
COMPANY NAME | Kelompok 3
DATE | 2023-09-26 | [5 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | % of TASK | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[6 empty] | COMPLETE | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Analisa dan Desain Sistem |  | 2023-09-26 | 2023-10-10
1.1 | Menganalisa Sistem Kepegawaian dengan melakukan wawancara kepada pihak yang ditunjuk | Ridha Akmal | 2023-10-11 | 2023-10-13 | 3 | 100%
1.2 | Project Charter | Fajar Febriansyah | 2023-10-03 | 2023-10-09 |  | 85%
1.3 | Gantt Chart | Johanda Lobianto | 2023-10-09 | 2023-10-16 |  | 20%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%